Center for Information Technology
and Development (CITAD)
Five-Year Strategic Plan: 2021-2025
Developed by CITAD with support from MacArthur Foundation.
Revised (November 2020)

TABLE OF CONTENTS …………………………………….2                                                     
LIST OF ABBREVIATIONS.  ……..
3
INTRODUCTION AND BACKGROUND
4
BRIEFS FROM CITAD EXECUTIVE DIRECTOR……………………………………………………. …5
CITAD BACKGROUND INFORMATION AND ORGANISATIONAL PROFILE                  6-    8

OPERATING ENVIRONMENT                                                                                             9-10.
SWOT ANALYSIS                                                                                                              10 -12.

VISION, MISSION AND CORE VALUES                                                                                  13

ACHIEVEMENT OF STRTEGIC PLAN FOR THE PAST TWO YEARS                               14-17.

STRATEGIC GOALS AND OBJECTIVES                                                                             18-19

CHART OF STRATEGIC GOALS, OBJECTIVES AND ACTIVITIES OF THE PLAN           20-38.
 M&E MATRIX   …………………………………………………………………..      39  -  55 
APPENDIX  1..RISKS AND ASSUMPTIONS………………………………………………….  ..56 
5APPENDIX 2: HISTORICAL SCAN ………………………………………………….   … 
7


1. List of Abbreviations

APC
Association for Progressive Communications

BOT
Board of Trustees 

CITAD
Center for Information Technology and Development 

CBO
Community-Based Organization

CSO
Civil Society Organization

DFID
Department for International Development

ED
Executive Director 

FCT
Federal Capital Territory 

FOI
Freedom of Information Act 

GB
Governing Board (of CITAD)

GBVO
Gender-Based Violence Online 

ICT
Information and Communication Technology

IT
Information Technology  
KSSMB    Kano state school Management Board
LEAD
Leadership, Empowerment, Advocacy and Development

LEEDS
Local Empowerment and Economic Development Strategies

LGA
Local Government Area

M&E
Monitoring and Evaluation 

MDA
Ministries, Departments, and Agencies
NECO
National Examination Council
NCC         Nigerian Communications Commission

NITDA      National Information Technology Development Agency
NDI
National Democratic Institute 

OCA
Organizational Capacity Assessment

PEST
Political, Economic, Social, and Technological

RTI
Research Triangle Institute

SEED
Sustainable Employment and Economic Development

SRIP
Sponsored Research Infrastructure Program

SWOT
Strengths, Weaknesses, Opportunities, and Threats

WAEC
West African Examination Council 

UK
United Kingdom

USA
United States of America

USAID
United States Agency for International Development.
1.0. INTRODUCTION AND BACKGROUND

1.1. Introduction

Strategic planning is a systematic process through which an organization defines its strategy or direction, builds commitment among key stakeholders, and makes decisions on allocating its resources to pursue this strategy. Strategic planning usually focuses on the entire organization. Simply put, strategic planning determines where an organization is going over the next year or more, how it is going to get there, and how it will know if and when it gets there. 
Various analysis techniques can be used for strategic planning, including strengths, weaknesses, opportunities, and threats (SWOT) analysis and political, economic, social, and technological (PEST) analysis, which were used for this process. The way in which a Strategic Plan is developed depends on the nature of the organization’s leadership, culture, complexity of its environment, size of the organization, and the expertise of planners.

A variety of strategic planning models are used to develop a plan (i.e., goals-based, issues-based, and organic). Goals-based planning, which is probably the most commonly used model, focuses on an organization’s mission and vision statements and core values; the goals to work toward to satisfy the mission, the strategies to achieve the goals, and action planning (who will perform what tasks and by when). Issues-based strategic planning examines an organization’s challenges, strategies to address those challenges, and action plans. This Strategic Plan combines the goals-based and issues-based models. 

Thisfive-year strategic plan was developed in 2018. Having implemented the plan for two years, it has become pertinent for CITAD to review the plan for the following purposes:

· Ensure that focus of the plan is maintained

· Ensure compliance with current social, environmental and technological development and determine progress made in the implementation of the plan(what worked and what did not work and why) 
· Determine changes that have occurred in the internal and external environment of CITAD

· Assess the aspect of the plan that needs to be removed and what needs to be retained

· Determine the need for new goals and strategies.

1.2. Brief Comments from CITAD’S Executive Director.

There are serious development challenges in Nigeria e.g. increasing economic contraction, rise in unemployment and deepening insecurity due to insurgency. These challenges can cause serious implications to the democratic process in the country. Information and Communication Technologies (ICTs) have the potential to make significant impacts in addressing those challenges. In particular, ICTs can be used to promote transparency and accountability, create jobs and wealth, enhance citizens’ participation in governance, and facilitate dialogue for national cohesion and unity.

The mission statement of the Centre for Information Technology and Development (CITAD) is to use ICTs to empower citizens for a just and knowledge-based society that is anchored on sustainable and balanced development. Consistent with CITAD’s mission statement and for ICTs to deliver on this potential, there is need to mainstream ICTs in the development agenda of the country. Mainstreaming ICTs requires increased awareness among ordinary citizens and policy makers about this potential and improved accessibility and affordability of ICT goods and services. Mainstreaming ICTs also requires universal ICT literacy in the country and an abundance of skills of staff for creating applications. In a basic sense, these requirements are the focus of the CITAD’s work in the next five years as outlined in this Strategic Plan.

Ensuring the mainstreaming of ICTs in the development agenda requires robust and sustained advocacy, coupled with programs to build awareness that inform people about why ICTs are important to the country’s development. Advocacy would also focus on the need for the government to take actions to increase the accessibility and affordability of ICTs in the country through appropriate policy, engineering and implementation. Citizens and government officials should be informed of new services and how these could be deployed and used. Government officials and civil society organizations (CSOs) would need an enhancement of their skills regarding the deployment of ICTs because this will assist them with their work and subsequently deepen the information society in the country.

CITAD would increase its advocacy efforts by offering awareness-building programs and providing training for basic user skills and advanced skills for the use of ICTs. Both government officials and CSOs would need to have better understanding of new ICT–based governance platforms such as e-Governance, e-Parliament, e-Tendering, and e-procurement. They would also need to know how these platforms could enhance good governance in terms of promoting transparency and accountability and improving citizens’ participation in governance processes. These programmatic concerns are included in this Strategic Plan for 2021 to 2025
The hope is that by implementing this Strategic Plan, CITAD will be positioned to contribute in a significant way to the development processes of the country and democratic consolidation.
1.3. Background and Organizational Profile
Centre for Information Technology and Development (CITAD) is a non-governmental and non-profit organization that is committed to the use of information and communication technologies for development and promotion of good governance. It was established first as a single project (Computer Literacy Project) in 1996 but was expanded in 2000 to include other projects. Now it incorporates six different thematic units. With head office in Kano, it has three other offices located in Abuja (FCT), Dutse (Jigawa State), Azare, (Bauchi State) Jamaare (Bauchi State) Itas (Bauchi state) and Bauchi (Bauchi State) as well as three outreach units located at Gombe (Gombe State) and Damaturu (Yobe). 
CITAD sees technology as a tool to promote sustainable development, good governance and peaceful coexistence. It uses ICT to empower youth and women through access to information, skills and online mentoring opportunities. It utilizes platforms such as social networking, web-to-text interface and tools such as Google alert to provide information that would promote peaceful coexistence. It uses Google alerts to source information about trends of discussion in various platforms, sites and online discussion lists and sites with a view to understanding trends, attitudes and positions such that it can develop appropriate responses to those that are similarly disseminated to either reinforce positive trends or counter and neutralize negative ones. Furthermore, CITAD uses ICT to partner with organizations in advocating for accountable, democratic and transparent governance in pro-poor policies and programs. Consequent upon these, it builds the capacity of poor and excluded people and communities to use ICT to demand for their rights. To make this a reality, it campaigns for affordable and inclusive access to ICT and materials for poor and excluded communities and works with government and corporate organizations to promote policies and practices that address the rights of poor and excluded communities to ICT.

1.4 AIMS AND OBJECTIVES OF THE ORGANISATION:
Its overall aim is to provide guidelines informed by both research and practice on how ICTs could be properly deployed in the efforts to promote sustainable development and good governance. Its broad objectives include:

i. Raise awareness about the use of ICTs in development

ii. Use ICTs as tools for the promotion of democracy and good governance.

iii. Propagate best practices in ICTs applications for the development

iv. Campaign for an appropriate national policy on ICTs

v. Conduct research on ICTs in development

vi. Run community computer resource centers for people to have access to computing facilities.
vii. Monitor the application of ICTs in the society.
viii. Provide training to disadvantaged groups such as women, children and other marginalized groups on ICTs.

1.5 Structural Units
CITAD has been structured under seven thematic units which include the following:
1. Training Unit

2. Technical Unit 

3. Youth Entrepreneurship 

4. ICTs for Peace Building

5. Internet and Digital Inclusion 

6. Governance Programs
7. Research 
2.  STRATEGIC FOCUS
CITAD’s strategic focus is categorized as follow:
a. Advocacy and Popularization: This involves working with journalists, ministry of education, teachers and students in schools, including annual ICT quiz for students, films for popularization of ICTs, Sensitization programs and using social media for advocacy. 
b. Training and Skills Provision: This covers basic ICT training at our various centers, customized training for our target groups, skills mentoring and online programs for continuous development of young entrepreneurs and ICT support for CSOs including training and website donation.
c. ICTs in Peace Building: This involves Social media peace campaign www.citad4peace.org.ng, www.citad.org, online monitoring and countering of hate speeches, engaging youth both in and out of school for peace building campaign and working with communities to enhance their resilience in confronting adversities.
d. ICTs in Governance: Election monitoring using ICT tools, mainstreaming citizens’ participation in budget processes using ICT and mainstreaming ICTs in governance. 
e. ICT-based Entrepreneurship.Training on both ICT and entrepreneurship skills, work in space for young entrepreneurship, E-mentoring scheme.
f. ICT Consulting services and business promotion: The organization provides consultancy services in all areas of ICT applications, and promotes business through ICT fairs and exhibitions, ICT business dialogues and the production of annual ICT year book dealing with ICT business development and market outlook in Nigeria.

g. Partnership and Networking: CITAD in collaboration with relevant MDAs and CSOs work to promote accountability in education governance in the NE, safety and security in schools and IDP camps in the North East and utilizes libraries as sites of development

h. Research: CITAD under takes research on various issues including: ICT and Development, ICT and Gender, Governance, Citizens Participation and ICTs, Human Rights Issues, Budget Performance, Conflict resolution and peace building. 
3. MAJOR BENEFICIARIES OF THE PROGRAMS OF THE ORGANIZATION
The major beneficiaries of CITAD’s programs are youth, women, excluded groups, civil servants, media groups, political parties, internally displaced persons (IDPs), CSOs and nongovernmental organizations. Others are faith-based organizations, and community-based organizations (CBOs) and educational institutions.
4.  PARTNERS AND FUNDING SOURCES
Since its inception, CITAD has enjoyed support from various organizations both Internationally and Nationally. Currently CITAD is partnering with the following Donor organizations and private sector organizations to implement its programs and expand its funding sources. They include:
MacArthur Foundation, Action Aid International Nigeria, National Democratic Institute (NDI), DFID (UK), United States Agency for International Development ( USAID), Women Enhancement Technology (WeTech) Association for Progressive Communications (APC), MasterCard Foundation, Managing Conflict in Nigeria (MCN), Centre for Research and Documentation, Kano State, Civil Society Legislative Advocacy Centre, Abuja, Centre for Democracy and Development (CDD), Intersystem Computer Services Limited, Kano State, Cybertech Ventures Limited, Kano State, Mediwat Computer Institute, Kano State., Fombina Imprints, Nigeria Internet Registration Association (NIRA). CITAD is also partnering with the following MDAs
· Ministries of education of Adamawa, Bauchi, Borno, Gombe, Kano, Taraba and Yobe States;
· Bauchi State House of Assembly, 
· Special Schools Management Board, 
· Bauchi State, State Universal Basic Education, Bauchi,
· Kano State Ministry of Commerce and Industries,
· Jigawa state Hotel, 
· Federal Ministry of Youth Development,
· Bayero University, Kano State, 
· Kano University of Science and Technology (KUST), Wudil

· Maitama Sule University, Kano 

· Jigawa State Ministry of Education, Science, and Technology, 
· Nigerian Communications Commission (NCC), 

· Nigeria Information Technology Development Agency (NITDA) and
· Kano State Ministry of Women Affairs  
Partnership with Private Organizations/Individuals
Many individuals have donated to CITAD specially to support its annual secondary schools quiz competition. Each year, CITAD staff and members have financially contributed to the organization.
5      CITAD’s Operating Environment 
Northern Nigeria has the lowest of all development indices in the country. In the education sector for example the north eastern part has worse education statistics. Male adult literacy rate is low with all states in the region having lower than national average rates. The north has also highest birth rates, and high maternal and infant mortality rates. Such high mortality rate is an indication of the poor status of women. Consistent with this premise, most women in the zone are economically dependent on their husbands or other male breadwinners and thus in the context of the economic crisis which has seen the incomes of families collapsing, women suffer most. A particular segment of women who are most vulnerable are those who are in purdah (seclusion). Because they are secluded, opportunities for economic activities and personal empowerment are very few. Poverty is most pervasive and extreme in the region. 

There is simultaneously high incidence of poverty and unemployment, resulting in a low human development index of 0.322 with a corresponding gender empowerment measure of 0.118 just slightly above that of North West (at 0.117) and far below that of North Central (0.244). Extremely poverty and unemployment have merged to create an army of unemployed untrained youths. Given that the region has also higher percentage of out of school children, it means that the states have the problem of having many people who are not able to fit well into the modern economy. It was these segments of the society that has formed the recruitment base of the Boko Haram insurgency in the country. The region has also one of the highest numbers of blind people as well as other categories of people living with disability. The poor performance of the states in the region of health and education are due to a combination of factors, some of which include: Poor governance, ignorance, low literacy level, ignorance and misconception. 
While recognizing the importance of ICTs in addressing these and many other development problems of the region and indeed the country, we must also acknowledge that access to ICTs is problematic. The country is characterized by different layers of digital exclusion and divide; along different lines the digital divide is even worse in the northern part of the country. While the national school curriculum has made computer studies compulsory at both basic and secondary schools’ levels, majority of public-owned schools do not have computer laboratories. They have no access to internet, they do not have the teachers to teach and even the few schools that have computer laboratories, they are not able to maintain them or even use them because they cannot afford the cost of fueling generators in the absence of stable electricity supply. This has not only made it impossible to make computer studies examinable subject in both WAEC and NECO but also render the policy of making it compulsory a mere paper provision. CITAD recognizes that there is need for a sustained advocacy on this. 

Access and use of ICTs are determined not only by availability but also predicated upon awareness of what ICTs can do. Many people, communities, institutions and government officials (if not governments!) do not appreciate enough what ICTs can do to address our development problems. To address this there is need for sustained campaign and awareness building. For this to be effective it must be driven by empirical evidence and research is thus necessary.

Research itself also helps to address certain critical questions in the application of ICTs for development. How do we deploy ICTs without unintended negative consequences? How do guard against the negative uses of ICTs such as gender violence online, spread of hate speech or its use for violent causes?  In this sense, we need to adapt appropriate and relevant policies, regulations, frameworks that will while maximizing the benefits minimizes the negative consequence. Finally, we must interrogate the global dimensions of the digital divide in which Nigeria is not only in the negative side of the divide but also a country which is more of consumer of ICT goods and services, with little or no production, in this we need to grow the sector so that ICTs goods and services can become more available, affordable and accessible to the citizens.

6   SWOT AND PEST ANALYSIS
6.1 Analysis of Trends.
  Table 1: Political, Economic, Social, and Technology Trends and Their Impacts (PEST)
	Political Trends
	Impacts

	· Transition or change in leadership
	· Suspension of ICT initiatives

	· Election crisis
	· Closure of offices and disruption of program implementation

	· Inclusion of computer subject as core course in senior secondary school syllabus
	· Increased demand for ICT training of both teachers and students

	· Government ICT project
	· Increased demand for ICT capacity development of staff

	· Delay in budget release and poor budget performance
	· MDAs unable to support ICT initiatives 

	Economic Trends
	Impacts

	· Poverty
	· Reduced patronage of ICT  activities

	· Poor electricity service supply
	· Increased overhead cost for training programs

	· Recession 
	· Slows down economic activities 

	· Joint account between LGAs and the state government.
	· Inability of the LGA to support its staff to access ICT capacity development and purchase IT equipment

	· Youth unemployment
	· Increased demand for entrepreneurship skills training

	Social Trends
	Impacts

	· Ignorance
	· Lack of knowledge among people about the importance of ICT in development; reluctance to be ICT literate

	· Resistance to change
	· Low uptake of ICT training and usage by the government and the private sector

	· Insecurity 
	· Affected the activities in some communities in the state by reducing program coverage

	Technology Trends
	Impacts

	· Paradigm shift from conventional to modern technologies
	· Increasing challenges to keep abreast of ICT development

· High demand for ICT skills


     6.2
Outcomes of the SWOT Analysis

       Table 2: Issues Identified During the SWOT Analysis

	Strengths
	Weaknesses

	· Office space at least in all the regions we operate i.e. Northeast, Northwest and North Central

· Large number of volunteers

· Adequate pool of ICT Professionals 

· Networking with CBOs and government agencies
· Competent personnel 

· Uniqueness
	· Inadequate training facilities and office equipment in some offices.

· Gender imbalance 

· Limited sources of revenue generation 

	Opportunities 
	Threats

	

	· High demand for IT skills

· Availability of IT companies 

· Availability of donor agencies 

· State-owned ICT programs

· Willingness to give financial Support to our women and Girls IT entrepreneurs by SMEDAN

· Existence of social investment programmes 

· Ecosystem (creating, maintaining and sustaining all relationship)

· Recognition and acceptance by donors’ agencies 

· Acceptance by host communities 
	· Power instability 

· Insecurity 

· High competition for grants 

· Poor political will by some government agencies 

· Hacking 

· Poor connectivity  




5. VISION, MISSION STATEMENTS AND CORE VALUES
a. Vision Statement:
A knowledge-based democratic and self-reliant society.  
b. Mission Statement
To empower citizens for a just and knowledge-based society that is anchored on sustainable and balanced development using ICT, Capacity Development, Advocacy, Research and Partnership,
c. Core Values: CITAD’s core values are built on the following principles: 
· Responsibility: We take responsibility for all engagements with our stakeholders.
· Responsiveness: CITAD listens and responds to the needs of its stakeholders
· Reliability: We live by our words.  
· Integrity: Our conduct is governed by the highest ethical standards.
· Transparency: We are open to public scrutiny in all our conduct.
· Accountability: We hold that every resource and action must be subjected to the test of accountability to our constituents, partners and supporters.
8. ACHIEVEMENTS OF GOALS AND STRATEGIC OBJECTIVES OF THE PLAN IN THE PAST TWO YEARS (2018 TO 2020).
Having implemented the strategic plan for two years, CITAD management and governing board deemed it necessary to review the plan to ensure that the plan focus is maintained, identify the level of goals and objectives achievement and include new goals to address emerging needs of CITAD’s organization.

The review process began with decision to review the plan which was reached during management meetings, preliminary review by CITAD management committee and inviting consultants to provide more technical support to complete the review.

Part of the review process was examining the goals to assess the number of goals achieved, identify those that were not achieved, identify challenges encountered in the implementation of the plan during the review period. Furthermore the process involved deciding what new goals and new strategies need to be added to the revised plan. 

The following table is an illustration of the achievements of the plan in the past two     years (2018 to 2020)  
          Summary of Achievements (2018-2020)
          Table 3: 
	Goals
	Achievements
	Challenges

	Strengthened resource base of CITAD.

	Resource mobilization plan developed
2 IT training centers and 1 ICT Academy fully accredited.
2 communities in Jama’are and Itas LGAs have had IT Centers established in collaboration with members of house of representatives from their constituencies.

	High inflation rate affected cost of Administration and implementation of activities such as community IT sensitization and maintaining administrative cost.

	CITAD’s organizational capacity strengthened.


	Staffing level has been improved by employing 6 program staff and some volunteers. All staff have had their capacity strengthened to enable them perform their responsibilities effectively. 
	

	Improved operational system for effective services delivery?

	CITAD operational policies have been reviewed to reflect its emerging needs. Equipment/programs put in place    to improve the organizational system include: solar system, online radio station and office furniture.

BOD has been reoriented on its functions. 5 board meetings took place within the review period.  

CITAD’s M&E unit been improved through development of M&E plan and employing M&E Officer

	

	Partnership and Linkages

	Collaborations have been strengthened with government agencies. For example, NCC and NITDA are supporting CITAD’s ICT quiz, social influencers summit and other activities, Kano state Ministry of Women Affairs rented a space for CITAD for the establishment of ICT Academy. CITAD is supporting Ministry of education Bauchi with capacity development in the area of ICT. Kano state Science board (KSSMB) is also supporting CITAD in its secondary school’s ICT activities.

	High expectation from government 
counterpart funding is usually not provided

	Expanding the scope of use of ICT in the North

	Advocacy, inter secondary schools ICT quiz, research on the availability and usage of ICT infrastructures in 85 girl secondary schools in Kano have been carried out. Findings of which will provide basis for advocacy for strengthening ICT component in the activities of the schools.
	The emergence of Corvid 19 and subsequent lockdown and closure of all schools impeded the continuation of in-schools ICT activities. 
-Government Bureaucracy frustrates CITAD efforts in schools ICT interventions.

	ICT Gender Gap reduction:


	Implementation of Creative Space for Women Innovators: The Gender Digital Inclusion component of its activities in 2018, embarked on the implementation of the ‘Creative Space for the Development of Young Women Innovators for Entrepreneurship. 44 participants in Abuja Digital Livelihood Project (DLP)

Over 250 participants drawn from 15 remote communities in the FCT, were trained in five centers, namely: Pasepa, Gaube, Leleyi Gwari, Tunga Ashere and Dakwa.
One of the outcomes of the project was that the participants were able to set up 20 new small-scale businesses, through which they are now able to provide steady supportive income for their respective families, which has gone a long way reducing joblessness among the young women.  
	Inadequate resources for entrepreneurship start up 


9. GOALS AND STRATEGIC OBJECTIVES OF THE PLAN.

This revised plan has seven strategic themes and nine goals with various specific objectives to achieve the goals.

Goal 1:  Improved resource base of CITAD

Strategic objectives:

· Increase the organization’s internal revenue generation by 10% annually
· Increase by 20% CITAD’s external resources
Goal 2: Strengthened CITAD’s organizational capacity   
Strategic Objectives:

· Reduce the organization’s staffing gap by 50% by 2025
· Strengthen the capacity of CITAD’s staff for effective performance
· Increase the staff motivation and retention.
Goal 3: Improved operational systems for effective service delivery

Strategic Objectives:

Ensure effective implementation of operational policies
Strengthen CITAD Governance structure

Strengthen M&E system for CITAD.
Goal 4: Strengthened CITAD’s partnership and linkages
Strategic Objective:

· To increase by 100% collaborations with MDAs, ICT organizations and IT companies for synergy
· Support uptake of research outputs by industries and government

Goal 5: Reduced Gender digital gap in CITAD target states.

Strategic Objectives:

· Increase by 20% number of girls’ secondary schools with functional ICT centers by 2025
· Develop the capacity of MDAs to mainstream gender in ICT programs

· Counter Gender-Based Violence online

· Increase by 20% digital literacy among women and girls in CITAD’s program locations.

Goal 6: Expand use of ICT scope in the country

Strategic objectives:

· Increase by 10% number of basic & secondary school teachers and government officials with ICT skills.

· Support ICT career development among students in higher institutions
· Increase by 60% number of poor and excluded communities using ICT to demand for their rights
· Increase by 20% ICT literacy among people living with disabilities.
Goal 7: Promote good governance using e-governance strategies.

Strategic Objectives

· Increase by 30% number of MDAs whose services and activities are accessible online
· Set-up 20 community networks to expand access to internet services for the underserved 

· Increase by 15% number of ICT initiatives for tracking public projects
· Develop the capacity of MDAs to practice e-governance
Goal 8: Peace promoted in conflict-ridden regions of the country
Strategic objectives:

· Improve capacity of 100 CSOs to monitor and counter online hate speech
· Promote peaceful coexistence and national unity

· Track kidnapping and communal conflicts in the country using ICT

Goal 9: Enhance self-reliance among women & youths
Strategic Objectives:

· Increase number of women & youths placed on gainful employment through CITAD intervention by 20% annually
· Increase by 30% number of women & youth entrepreneurs through CITAD interventions 
 10. Strategic Goals, Objectives and Activities.

Table 4:                             Goal 1:  Improved the resource base of CITAD
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	1.1 Increase the organization internal revenue generation by 10% annually


	-Establish ICT Academy in Kano


	· Acquire license

· Design the academy

· Build 6 classrooms, 6 offices, 1 Library, sick bay, cafeteria 

· Landscape the academy

· Purchase 50 computers, borehole, 10KVA generator, V-SAT5-MB bandwidth   

· Staffing

· Put in place the marketing strategies renting of shop
	2021


	Training Coordinator



	
	Establish Computers & Accessories Shop


	Procurement of computer accessories and staff engagement to man the shop.
	
	

	
	Running consultancy service
	· Register company 

· Advertise services online
· Courtesy calls 

· Develop prequalification documentations
	2021


	Accountant 

	1.1 
	Establish event center.


	· Get the permit, 

· Build the structure, 

· Employ staff to manage the center 

· Procure equipment and facilities. 
	2021


	Training officer/Social media officer

	
	Use online radio station to generate revenue


	·  Map out prospective audience and clients
· Develop marketing strategy
· Market online radio services through social media platform
	2021-2025
2021-2025
	Radio Coordinator

Treasurer 

Program Coordinator

	1.2 
	Rent out Hostel


	· Produce an architectural design 
· Structure the house 
· Conduct feasibility study 
	
	

	1.3 
	Establish waste collection services (general & e-waste)


	· Identify collection centers
· Procure collection containers

· Staffing

· Procurement of Vehicles
	
	

	1.2 Increase by 20% CITAD’s external resources


	Develop solicited and unsolicited proposals
	· Build Capacity of staff on resource mobilization & proposal development

· Search for new funding opportunities 

· Write and submit proposals

· Follow up on submitted proposals
	2021-2025


	Senior program officer



	
	- Conduct fundraising

Partnership development
	· Write solicitation letters to ICT related companies
· Establish e-wallet platform for receiving donation
· Identify collaborating partners

· Identify resources to 
leverage upon 
	2021-2025


	


Goal 2: Strengthen CITAD’s organizational capacity
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	2.1 Reduce the organization’s staffing gap by 50% by 2025


	-Evaluate staff strength


	· Carry out staff audit 

· Conduct workload analysis
· Employ or deploy staff
	By end of 2021

	Human resource officer



	
	Recruit staff to address the staffing gap
	· Advertise for the vacant positions

· Conduct interviews

· Recruit the qualified staff

· Conduct staff orientation 

· Develop their capacity
	By end of 2021
	Human resource officer

	2.2 Strengthen the capacity of existing CITAD’s staff through addressing various staff capacity needs by end of 2021


	-Annual Staff Appraisal

Conduct trainings to address capacity gaps
	· Review the staff appraisal tool
· Conduct staff appraisal

· Develop capacity building (CB) plan
· Train staff according to capacity needs using the CB Plan
	2021-2025

2021-2025

	Human resource Officer

Human resource Officer

	2.3 Enhance staff motivation and retention through implementing reward systems by end of each year
	-Review staff emolument packages.

-Review staff reward system

	· Review job descriptions

· Provide competitive incentive package
· Implement new reward system. (e.g commendation letters, prizes and or salary increase) 
	2021-2025


	Human resource Officer


Goal 3: Improved management systems for effective service delivery
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	3.1 Increase implementation of operational policies from 65% to 85%.

	-Review the operational policies 


	· Conduct policies implementation audit
· Make the policies available to staff for familiarization and compliance
	2021-2025
	M&E Officer

	3.2 Strengthen M&E system for CITAD

	-Develop a harmonized operational CITAD data base.
-Conduct operations research

-Use ICT related research findings in programming
	· Develop M&E plan 
· Develop annual operational workplan 
· Develop result frame work for the organization
· Form research team with clear ToR

· Assign operation research team leader

· Collaborate with research institutions to conduct ICT related researches

· Share research findings among stakeholders during meetings, press conferences and advocacy visits.
· Publish research reports online
	2021

2021-2025


	M&E Officer

	3.3 Strengthen CITAD Governance structure by the end of 2nd quarter of 2021
	-Develop CITAD’s sustainability plan


	· Review board manual

· Conduct board reorientation
· Strengthen the capacity of board members on e-meetings

· Conduct quarterly board meetings

· Develop CITAD’s succession plan
	End of 1st quarter of 2021
	ED


Goal 4. CITAD’s partnership and linkages strengthened
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	4.1. To increase by 100% collaborations with MDAs, ICT Organizations and ICT companies for synergy


	-Create data base of collaborating partners in the operating environment.

-Conduct advocacy visits to existing and prospective collaborating partners 

- 

	· Develop data capturing form for MDAs, ICT organizations and ICT companies in the Country.
· Map out existing potential collaborating partners (MDAs, ICT organizations and ICT companies in the Country).
· Write letters of introduction and request for partnership and collaboration with the partners.
· Develop annual collaboration activity calendar. 

· Share CITAD publications.
· Hold collaborating meetings.
· Partner in hosting events or commemoration /celebration of special days.
· Knowledge/information/facilities/materials sharing.
	2021-2025

2021-2025


	Senior Program Officer

	4.2. Support uptake of research outputs by industries and government


	-Disseminate key research findings to relevant/prospective users.
-Monitor use of research outputs.

	· Identify and profile relevant research findings from research institutions.
· Share findings with relevant government MDAs and other partners.
· Request progress reports.
· Visit organizations to assess use.
	2021-2025


	Research Officer


Goal 5: Gender digital gap in the Country reduced.
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	5.1 Identify the factors influencing low utilization of ICT and internet services by women and girls in CITAD’s target states
	-Conduct research to identify the factors influencing low utilization of ICT and internet services in the target states

 
	· Development of research tools.
· Identification of research teams.
· Documentation of and dissemination of research findings.
· Monitoring of gender-based violence online.
	By end of 2021
	Research coordinator

	5.2 Increase by 20% number of girls’ secondary school with functional ICT centers by 2025


	-Assessment of ICT facilities in girls’ secondary schools.
-IT skills baseline assessment 

-Gender sensitization activities
-Gender mainstreaming in ICT programming


	· Advocacy for increased access to ICTs especially for young girls in schools.
· Conduct of baseline assessment.
· Sensitization of women and girls on the importance of digital skills

· Train MDAs and schools Head on gender mainstreaming in ICT programming.
	Ongoing
	IT Coordinator


	
	ICT training of women and girls.
	· Develop training module

· Identify the participants
· Produce training materials and deliver the training programs


	
	

	Promote digital inclusion in CITAD target states by end of 2022
	-Carry out research on different dimensions of the digital divide 


	· Develop the suitable research design and identify the tool
· Select research subjects
· Provide funds and other materials to conduct the research.
	
	


Goal 6: Use of ICT in Nigeria Expanded
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	6.1 Increase by 25% number of secondary schools with ICT teachers and ICT laboratory  


	-Conduct a survey of the ICT facilities and teachers with ICT skills in schools of the target states,


	· Identify target schools

· Advocate for support for the survey from stakeholders

· Develop or adapt survey tools
	June 2021
	Training unit 


	6.2 Increase number of schools reached with ICT career intervention by 30% 


	-Liaise with the Ministry of education and secondary schools’ boards (in the case of some states) to reach out to the schools for career talks.


	· Send career talk introductory letters to the target schools 

· Conduct career talks in the schools.

· Identify ICT skilled teachers to provide the mentoring 
· CITAD to support the mentoring process to interested students 


	June 2021
	Training/technical unit 

	6.3 Increase by 60% number of poor and excluded communities to use ICT to demand for their rights


	-Expand CITAD training scope

-Assess the rights demanding gap in the communities.

-Capacity building on ICT to the poor and excluded


	· ICT sensitization of the target communities.

· Design training that will meet the demand of the communities 

· Conduct training in the communities 
	June to August 2021
	Programs Coordinator 

	6.4 Set-up 20 community networks to expand access to internet services for the underserved 


	- Identification and mobilization of 20 CSOs within CITAD network to expand access to Internet services for the underserved

-Advocate to NCC and NITDA to support the underserved communities. 

- Mobilize underserved communities on how to seek for support from the relevant stakeholders, e.g NITDA, NCC etc
	· CITAD to provide support to ICT centers setup by the relevant stakeholders.
· Revive soft loans option (Computer Loans) initiative of the organization
	
	Programs Coordinator

	Increase by 50 % above baseline level number of young people using apps in election monitoring 


	-Make the a-Hub functional in the target states

-Identify technical mentors 

-Begin apps development sessions 

-Identify CSOs that need training on new apps for elections observation 

-Conduct training 

-Identify best and emerging practices in the use of ICTs for election
	· Advertise for participation in a-Hub

· Select potential participants and invite them for discussions of the new ideas.
· CITAD to provide the necessary technical guide and mentoring

	biannually
	


Goal: 7 Good governance promoted using e-governance strategies
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	7.1 Increase by 30% number of MDAs in the target states whose services and activities are accessible online


	Conduct survey on number of MDAs with functional websites, organizational email addresses and social media platforms
Advocate for proper and effective utilization of IT tools
Develop Website for MDAs 

Host Website for MDAs


	· CConduct campaigns to the general public to demand for MDAs services online.
· DDevelop and send a partnership proposal to MDAs

· TTrain the MDAs staff on IT tools, managing websites and social media tools
	March 2021
Bimonthly

	Training Coordinator


	7.2 Increase by 15% number of ICT initiatives to strengthen MDAs on e-governance and public expenditure tracking.

	Develop the capacity of MDAs on e-Governance.
Domestication of apps use in tracking public project. 

- Mobilize MDAs to be updating their website by uploading relevant and current information as enshrined in the open governance partnership (OGP) Document
Conduct advocacy for increased use of ICTs for the conduct of elections in the country

	· Assess e-Governance capacity gaps of -MDAs 

· Design training needs for the MDAs on the identified gaps.

· Conduct sensitization lectures on e-Governance to MDAs
· Provide mentoring support to MDAs to achieve the implementation of e-governance strategies.
· Advocate to NITDA and NCC for technical support for   MDAs for the actualization of e-Governance
· sensitize MDA staff on the importance of use of ICTs in election processes

· capacity building of the electoral body on use of ICT in the election process

	Quarterly


	Senior Program officer




Goal 8: Peace promoted in the northern region of the Country
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	8.1 Improve capacity of 100 CSOs to monitor and counter online hate speeches

	-Training of civil society groups and media on use of ICT for peace, monitoring and countering of online hate speeches. 

-
Advocacy visits to security agencies, political and traditional leaders, religious leaders and celebrities on peace promotion.

	· Identify the CSOs to be trained 

· Design and conduct the training 
· Provide monitoring Support

· Design policy brief on the report provided to engage policy makers

· Develop campaign message
· Conduct training on Advocacy for peace campaign

· Design and conduct the advocacy
· Conduct follow up advocacies
· Monitor and track successes and document same

· Provide mentoring support.

· Share success with stakeholders

	2021-2025
	Programs Officer, Peace and Training Coordinator 

	
	
	· 
	
	

	8.2 Develop the capacity of 50 secondary schools and 20 tertiary institutions to establish peace clubs in their respective schools 


	-Establishment of peace clubs in secondary schools and tertiary institutions.

Capacity building of the students on peace building.
-Students competition on peace promotion initiatives


	· Identification of schools for peace clubs.

· Advocacy to schools and tertiary institutions heads to support the establishment of the peace clubs
· Quarterly lectures on peace by identified speakers.
· Meetings and sensitization of club members

· Provision of notice board for pasting of peace messages

· Creating website for peace clubs.

· Social media pages and groups for peace campaign messages

· Call for application entries
· Screening and marking for applications
· Awarding of prizes
	2021-2025
	Gender Officer



	8.3 Promote safety online for women and girls in the project regions

	-Organize Training programs for women and girls on safety and security online 

Sensitization of communities on security and safety online.
	· Identify participants for the training

· Identify the training manual and other training materials

· Identify venue and send out notification

· Conduct the training.
· Plan with the communities and women organizations the sensitization programs.
· Identification of women and girls in the target communities
· Conduct sensitization programs on safety and security online
	ongoing
	Program Officer, Gender


 Goal 9: Enhanced self-reliance among women & youths
	Objectives
	Main Activities
	Sub-activities 
	Timeline
	Who

	9.1 Increase number of women & youths placed on gainful employment through CITAD intervention by 20% above baseline level annually


	Improve the Job Placement and Information Service Program (JOPIS) programs


	· Engage more influencers to CITAD’s social media platforms to be able to see opportunities shared
· Reach out to other out sourcing companies for partnership 
	2021-2025
	Program Officer

	
	Leverage CITAD partnership with jobber man to get more youth and women employed 


	· Get more youths to register with the   Jobberman platform through training and sensitizations
	
	

	
	Conduct many entrepreneurship trainings

Maintain contact with the trained entrepreneurs for mentoring and additional capacity building 


	· Source more grants for trainings such as the Digital Livelihood skills trainings.

· Engage more mentors to the CITAD e-Mentoring platform.


	2021-2025
	Program Officer


11.         M&E MATRIX

Goal 1: CITAD’s resource base improved
	Activity
	Inputs
	Outputs
	Outcomes
	Impact
	Timeline

	Establishment of ICT Academy
	License for building the structure
Staffing

equipment/facilities 

funds to run the academy
	Academy established
	Income being generated
	CITAD resource base improved
	By end of 2021

	Establishment of Computer Accessories Shop


	Funds to rent the shop

procurement of

computer accessories

Recruitment of staff to Mann the shop


	Shop established


	Income generated 


	CITAD resource base improved


	By end of 2021



	Running consultancy services 


	Website development, research on ICT in target states.
Advertisement of CITAD services through online and radio programs 


	CITAD consultancy services established and being utilized


	CITAD income improved


	CITAD resource base improved


	Ongoing



	Establishment of event center

	Get the permit, build the structure, 

mobilize staff to manage the center, provide equipment and facilities. 

 
	Event center established 

	Center functional 

CITAD revenue source improved


	CITAD financial strength improved and sustainability guaranteed
	By 2nd quarter of 2022



	Establishment of Waste collection center


	Waste collection sites and vehicles, staff and funds.
	Waste collection center established
	Income being generated from waste collection
	
	By November 2021

	Proposal and partnership development


	Train staff on proposal writing
	Proposal drafts produced
	Programs adequately funded
	Financial status of the organization strengthened and sustainability ensured 
	Annually and as the need arises or opportunity strikes 


Goal 2: CITAD’s organizational capacity strengthened
	Activity 
	Inputs
	Output
	Outcomes
	Impact
	Timeline

	Conduct of staff audit and staff workload analysis to assess CITAD staffing needs and staff workload.

	Auditors

appraisal tools

funds and other materials
	Staff audit report 

Staff workload ascertained
	CITAD staff needs determined and addressed by employment or deployment.
	Improved staff performance with staff efficiency and achievement of organizational goals.
	

	Strengthen the capacity of existing CITAD’ s staff through addressing various staff capacity needs 


	Staff appraisal

Appraisal tools

Capacity development plan

Training manual
	Appraisal report

Capacity needs identified

Training conducted based on identified needs
	Staff training needs addressed CITAD staff capacity enhanced
	Improved staff performance with Staff efficiency and achievement of organizational goals.
	Third quarter of every year

	enhance staff motivation and retention through implementing reward systems 
	Staff retention policy
Staff retention plan


	Rewards system

established
	Staff motivation enhanced
	 staff retained and performance improved
	Annually




Goal 3: CITAD.s operational systems improvedfor effective service delivery
	Activity 
	Inputs
	Output
	Outcomes
	Impact
	Timeline

	
	
	
	
	
	

	Update operational policies and implement accordingly every operational year
	Policy documents
Review team

Material resources
	Revised policies in place 
	Revised policies being implemented
	System effectiveness improved. Project goals being achieved.
	Annually

	Provide adequate office equipment and communication facilities
	Funds
Material resources
	Office equipment secured
	Work environment improved
	System effectiveness improved and staff motivation increased.
	By 2nd quarter of 2021

	Improve the performance of CITAD’s BOT by building

their capacity annually over the plan period
	Training manual
Consultants

Venue

Training materials 

Funds
	Training report
Number of BOT members trained
	Improved BOT performance
	CITAD organization 
Strengthened for quality services
	Annually

	Ensure that CITAD sustainability Plan is in place by the end of 2021.

	Identify and customize samples of sustainability plan
	Sustainability plan developed or customized
	CITAD organizational structure sustained 
	CITAD growth increased
	

	strengthen the M&E system to monitor organizations performance
	 Annual operational workplan and M&E result frame work for the organization.

Develop M&E monitoring plan 


	M&E result framework in place
	M&E performance monitoring plan being used to track organization performance
	Organizational goals achieved
	


Goal 4: CITAD’s partnership and linkages strengthened
	Activity
	Input
	Output
	Outcome
	Impact
	Timeline

	Create database of collaborating partners in the operating environment.


	Donor/CSO assessment forms

Computers

Funds and other materials


	Donors and CSO Partners in CITAD.s operating regions identified


	Data base of collaborating partners developed


	CITAD Collaboration with Donors and CSOs Strengthened for synergy and sustainability.


	By July 2021

	Conduct advocacy visits to the collaborating partners (Donors, IT companies and NGOs/CBOs) and MDAs

	Write courtesy letters to the MDAs and IT companies

Develop advocacy kits
	Appointments for advocacy visits secured.
	Advocacy visits to all of the targeted MDAs conducted. Collaboration initiated
	CITAD partnership and linkages strengthened for better performance
	

	Implement collaborative programs
	Details of partners available 

Contact made with them and Possible collaborative programs   identified and developed 
	Collaborative Programs implemented 
	Objectives relying on collaborative programs being realized 
	Sustainability of the organization strengthened 
	


Goal 5: Digital gender gap reduced in CITAD’s target states.
	Activity  
	Input
	Out put
	Outcome
	Impact
	Timeline

	Advocacy Visit to relevant MDAs on the need to increase number of women and girls with digital skills
	Advocacy kits
Advocacy team
Funds 


	Advocacy conducted, advocacy report produced

	Support for increasing number of women with digital skills gained.


	ICT gender gap addressed. Women and girls utilizing ICT Skills for self and economic development


	Annually over the Plan period

	Assessment of ICT facilities in girls’ secondary schools.

IT skills baseline assessment 


	Identify target schools 

ICT assessment tools

Assessment teams

Funds


	Assessment report


	ICT gender gap among Girls in secondary schools of target states identified


	ICT gender gap addressed. Women and girls utilizing ICT Skills for self and economic development
	

	Gender sensitization activities

Gender mainstreaming in ICT programming


	Assessment reports

Gender sensitization messages


	Relevant MDAs reached with sensitization messages


	Support gained from Relevant MDAs on the need to increase number of women and girls with ICT skills 


	ICT gender gap addressed. Women and girls utilizing ICT Skills for self and economic development
	

	Sensitization of women and girls on the importance of digital skills


	Prepared Sensitization talks 

Venue

Snacks for participants
	Women and girls in target communities sensitized on the importance of digital skills 
	Positive attitude towards ICT utilization among women and girls developed
	Women and Girls utilizing ICT Skills for self and economic growth
	

	Training of women and girls on digital skills 


	Training advert

Training manual

Trainers

Trainees

Training materials

Meals
	Number of women and girls trained

Training report 
	Number of women and Girls with ICT skills in the target states increased above the baseline level


	Utilization of digital skills among women and girls increased.
Digital gender gap reduced
	

	Research and monitoring of gender- based violence online 


	Computers

Research tools

Research subjects


	Research conducted and findings documented
	Research findings utilized to design suitable programs to address GBV
	Gender based violence reduced
	

	Training programs for women and girls on safety and security online 


	Training manual
Identified women and girls participating in the training

Training materials

Funds
	Training report
Number of women and girls trained
	Women and girls empowered with online safety skills
	Women are empowered to protect themselves against Gender based violence  
	

	Carry out research on different dimensions of the digital divide agenda for the country 


	Computers

Research tools

Research subjects

Collaborating partners to conduct the research

Material and Financial resources
	Research findings

Research report
	Reasons for digital divide identified

Regions with low digital skills identified

Programs designed to address the digital divide developed.
	Digital divide between one region and the other in the country addressed


	

	Advocate for digital inclusion targeting relevant MDAs and CSOs
	Develop advocacy campaign message using data on percentage of physically challenged people that are digitally excluded

Identify physically challenged individuals and CSOs that will participate in the campaign
	Activity report
	Relevant MDAs and CSOs sensitized and mobilized to support digital inclusion
	Participation of physically challenged in digital activities enhanced   and digital inclusion achieved.
	


 Goal 6:  Use of ICTs scope in the northern states expanded 

	Activity  
	Input
	Out put
	Outcome
	Impact
	Timeline

	Conduct a survey of the ICT facilities and teachers with ICT skills in schools of the target states,


	ICT Need assessment forms

Target schools

Funds 


	Assessment report, 

	Schools with ICT facilities and teachers with ICT skills identified and documented


	Survey findings will inform decisions made to expand the use of ICT among students and teachers


	By end of 2021

	Liaise with the ministry of education and secondary schools’ boards (in the case of some states) to reach out to the schools for career talks.


	Career talk Introductory letters to the target schools 

Identified Speakers

Venue, funds

Carrier talk guide
	Reports of carrier talks

Target students well sensitized on ICT carrier option


	Sanitized students have developed positive attitudes towards ICT as a carrier option

	Self-reliance in young people developed

	2nd quarter 2021

	Provide mentoring support to the interested students 


	report

Training manuals

Training materials
	Trained teachers and Government officials from relevant MDAs
	ICT skills developed in students and MDA officials of the target states

	Technological development in students enhanced
	Ongoing

	Expand access to internet services for the underserved

 
	ICT training needs assessment guide

Resource person

Stationaries

	Community needs assessed and report produced

	Community ICT training need assessed and documented

	Assessment report utilized to design programs to address ICT training needs.


	Ongoing


	Advocate to NCC and NITDA to support the underserved communities. 


	Advocacy Kit

Advocacy team


	Advocacy report


	Cooperation and support of NCC and NITDA towards supporting the underserved communities gained
	ICT needs of Underserved communities adequately addressed
	

	Mobilize underserved communities on how to seek for support from the relevant stakeholders, e.g NITDA, NCC etc

	Training manual on advocacy and lobbying

Training material

Funds

Target communities


	Activity reports


	Communities empowered with lobbying and advocacy skills
	Underserved communities receiving support from NCC and NITDA to develop their ICT skills for achieving their rights


	

	Expand CITAD training scope


	Funds to upgrade CITAD training centers


	CITAD training centers upgraded and expanded


	CITAD training centers 

expanded to increase access to ICT training to rural poor and excluded in the target states
	CITAD resource base increased
	

	Assess the rights demanding gap in the communities.

Capacity building on ICT to the poor and excluded


	Assessment tool

Training manual designed to suit the rural populace


	Reports of assessment, and training rights demanding gap identified

Capacity building conducted


	Target communities empowered with advocacy and lobbying skills to utilize ICT Skills to demand for their rights


	ICT entrepreneurship among target rural communities enhanced. Economic status of the target group improved


	

	Identification and mobilization of 20 CSOs within CITAD network to expand access to Internet Services for the underserved

	Identified CSOs

Funds and mobilization materials
	CSOs sensitized and mobilized to expand access to internet services for the underserved in their areas of operations.
	Underserved communities have increased access to internet services
	ICT services are expanded in CITAD target states with resultant enhanced technological development
	

	Advocacy to State Ministry of education and schools’ principals to gain support for the inter school ICT quiz.
	Advocacy message

Advocacy team
	Advocacy report


	MDA and School principals support for interschool ICT Quiz schools gained.

Participating schools identified
	Students motivation to learn and utilize ICT skills enhanced
	Biannually

	Organize annual inter school’s ICT quiz competition
	Venue

Participating students

Quiz questions

Resource persons

Quiz prices
	Conducted quiz report

Participating school’s attendance sheet
	Students’ knowledge of ICT increased 
	Students motivation to learn and utilize ICT skills enhanced
	

	Advocate for affordable and accessible ICT training in poor and excluded communities. 


	Identify target communities

Prepare advocacy message

Identify advocacy team
	Advocacy conducted and advocacy report produced
	 ICT Centers in poor and excluded communities identified.

Communities resources committed to support the ICT training 
	Communities access to ICT increased
	


Goal: 7 Good governance promoted using e-governance strategies
	Activity
	Inputs
	Outputs
	Outcomes
	Impact
	When

	Conduct survey on number of MDAs with functional websites, organizational email address and social media platforms.


	Survey tools
Survey team

Funds
	Number of MDAs with functional MDAs identified
	Assessment report documents secured and will be utilized to design programs to address the gaps identified
	Job efficiency and systems strengthening achieved
	Last quarter of 2021

	Conduct sensitization campaign on importance of functional website in MDAs


	Sensitization messages
Funds and materials


	MDAs Sensitized on importance of maintaining functional websites
	MDA s maintaining functional websites
	Job efficiency and systems strengthening achieved 
	

	Develop the capacity of MDAs on e-Governance


	Training manuals on e-governance
E-governance policy documents

Funds and training materials
	MDAs trained on e-governance
	MDAs implementing e-governance strategies being implemented by MDAs
	Good governance achieved
	Ongoing

	- Advocacy to NITDA and NCC for supporting MDAs for actualization of e-governance
	Advocacy kit

Funds


	Advocacy report

	NITDA and NCC support to MDAs to achieve good governance gained
	Good governance strategies implemented by MDAs and good governance achieved.
	Ongoing

	Training of CSOs on use of apps for 
election monitoring 


	Training manual 

Identify CSOs

Resource persons

Training materials

 Financial resource
	Training report

Trained CSOs
	CSO using relevant apps for election monitoring
	Credible election conducted leading to improved governance
	Annually

	Training of CSOs and youth in the use of social media for advocacy 


	Training manual 

Identified CSOs

Resource persons

Training materials

Financial resource
	Training report

Trained CSOs
	CSO using social media for advocacy
	CSO performance enhanced
	

	Advocacy for increased use of ICTs for the conduct of elections in the country 


	Identify electorate bodies to be targeted with the advocacy

Develop advocacy message

Advocacy team
	Electoral bodies targeted with the necessary advocacy message
	Positive attitudes towards use of ICT for conduct of election developed in the electorate’s bodies
	Quality elections conducted

Transparency and accountability in governance increased
	


Goal 8: Peace promoted in the North east and North west region using ICT strategies

	Activity 
	Inputs
	Output
	Outcomes
	Impact
	Timeline

	Training of civil society groups and media on use of ICT for peace, 
monitoring and countering of online hate speeches. 

Advocacy visits to religious and traditional rulers to support the peace initiatives


	Identify participants

Training manual

Training Materials

Finances
Mentoring guide
Mentors

Functional websites

Advocacy kit

Advocacy team

Funds and material 


	Trained CSOs and media groups

Training report
CSOs are well guided and mentored to counteract hate speeches online
Religious and traditional leaders support for peace initiatives gained


	Trained participants utilizing knowledge and skills to advocate for peace in the target states
CSOs tracking and countering hate speeches online

Peace initiatives fully supported by religious and community leaders leading to reduced conflicts in CITAD project regions


	Peaceful coexistence achieved in the target states, region and the country at large
Peaceful coexistence achieved in the target states, region and the country at large
	Ongoing

	Establishment of peace clubs in secondary and tertiary Institutions


	Identified participating schools and club members

Training the members on establishment of the clubs

Identification of club activities
Funds to conduct club activities
.


	Peace club established in target schools in the north and west region of the country
	Peace club functioning to promote peace among students by conducting quarterly lectures on peace by identified speakers.

Posting of peace messages and creating website for peace clubs
	Peaceful coexistence achieved in the target states, region and the country at large
	

	Online monitoring and countering of hate speeches
	Established websites

Peace messages

Hate speech trackers

Student for peace groups.
	Tracking online hate speeches and neutralizing them

Dialogue meetings with religious leaders
	Hate speech Curbed 
	 Peaceful coexistence and national unity achieved.
	Ongoing


Goal 9: Self reliance among young people in the targeted states enhanced.
	Activity
	Inputs
	Outputs
	Outcomes
	Impacts
	Timeline

	Expand access to job opportunities through JOPIS programs


	CITAD social media platform
Identify youth to register with the Jobberman platform 

	Access to Job opportunities for young people improved
	Young people accessing jobs and self-reliance achieved
	Improvement of economic status of young people and the community at large
	Ongoing

	Advocacy to Ministries of Youth, education and women affairs.

On youth empowerment schemes
	Advocacy kits
Identify collaborating partners to support the advocacy, e.g women and youth CSOs
	Advocacy report

	Support for women and youth empowerment schemes achieved
	Relevant MDAs committed to helping women and Youths to get employment opportunities
	2021 to 2025

	Identification of beneficiaries in the target communities for Youth empowerment schemes


	Meeting with community leaders

Source for the beneficiaries

Develop criteria for eligibility
	Youth and women empowerment schemes beneficiaries identified
	Women and Youth linked to economic empowerment schemes
	Self-reliance achieved
	

	Skills acquisition Trainings and linkages of 

trainees to mentors for take-off grants


	Identify training needs through assessment

Select appropriate training modules

Identify suitable training outfits and make the necessary linkages. 
	Training report

.
	Women and youths entrepreneur skills developed necessary linkages for grants or job opportunities made
	Youth and women empowered for economic development and self reliance
	Annually through the plan period

	Reach out to other out sourcing companies to make partnership

	Online search for employment opportunities for women and youth

Provide the necessary linkages 
	Employment opportunities identified

Necessary linkages made
	Youth and women in the targeted states benefitted from the par
	Women and youth economic empowerment achieved.
	Ongoing.


Appendix 1: RISKS AND ASSUMPTIONS
Several factors will affect the implementation of this plan. These include: economic, political, environmental, social and technological factors. Assumptions are necessary conditions for achieving success at different levels of a strategic plan. Risks on the other hand are potential occurrences or events that are beyond the control of the organization and that would adversely affect the achievement of desired results. Risks can necessitate the change of strategic direction and approaches of the plan. However, CITAD is optimistic that the new strategic approaches in this plan will overcome the anticipated challenges.
	Assumptions
	Risks

	CITAD has an effective leadership and BOT that will mobilize resources for the organization to achieve the strategic plan goals
	Heightened insecurity in the northern region can cripple CITAD activities and affects achievement of its goals

	CITAD has gained broad base recognition among the MDAs and IT companies in Nigeria. This strengthened partnership will provide CITAD with great opportunities for collaboration and growth
	Inflation rate: Current inflation rate will have huge implication for running costs and procurements. ICT hardware are usually very expensive

	Increased demand for ICT will necessitate CITAD to open more training centers and that will improve the resource base of the organization
	Impact of Corvid-19 on the education sector has disrupted schools’ programs and CITAD plan to reach out to schools with its programs.

	Uniqueness of CITAD operation in its target states makes it special and attract patronage by young people and MDAs
	Corruption and its related problems can impact negatively on CITAD programs.

	
	Low literacy level and vulnerability of women and youth in the target states of CITAD’s operation

	
	Poor ICT infrastructure in especially northern Nigeria

	
	Most ICT initiatives are in the south 

	
	Private sector ICT companies are not encouraged and adequately supported by the government in northern Nigeria


Appendix 2: Strategic Planning Process.

Buy-in Process

CITAD was supported by RTI/LEAD to develop a five-year strategic plan (from 2018 to 2023). The need to develop the strategic plan was identified during the organizational capacity assessment supported by LEAD. Having observed the absence of strategic plan as a major capacity gap, LEAD built the capacity of CITAD to develop a quality strategic plan that will move the organization forward. This was achieved through training, technical support and mentoring.  The partnership between CITAD and LEAD has led to improved organizational capacity of CITAD. 
Strategic Planning Meeting and Workshop

The strategic planning process involved series of capacity building trainings and meetings. The first step was a four-day training of CITAD staff and other LEAD CSO partners in 2018.The purpose of the workshop was to increase the participants’ understanding of strategic planning and to discuss the importance of strategic planning for their respective organizations and its potential impact on service delivery. At the end of the workshop, participants developed a draft copy of a Strategic Plan for their respective organizations, that was further developed into full document by CITAD’S Strategic planning committee and with technical support of RTI/LEAD. Subsequently, CITAD set up an internal committee which worked and produced the draft Strategies Plan.  The draft was shared with staff, management and members of the board of the organization whose inputs further enriched the draft. The improved draft was then subjected to a review by the joint CITAD/RTI Committee. The process also benefited from the support of the USAID through SACE which provided consultants who looked through the draft and made further inputs as well as a presentation of the further improved draft to a joint Management/Board Committee meeting of the organization for final approval. The process ended with editing sessions.

Historical Scan

A historical scan of CITAD from 2011–2016 revealed that a lot of developmental events had occurred in the organization. The organization has expanded from its founding base in Kano to have offices in Jigawa and Bauchi states as well as in the Federal Capital, Abuja. It has over 12 training centers distributed across the three geo-political zones it now operates. Two of these centers were established by a legislator who handed them to CITAD while five

others were set up through a support of a partner CSO. Its programs have expanded to cover the whole of the country, although it is still deeply rooted in its core areas of operation which are the northeast and northwest zones of the country. 

Institutionally, it has endeavored to meet its most corporate requirements. It has yearly filed its annual returns to the Corporate Affairs Commission (CAC), obtained SKUL registration, accredited by the Computer Professionals Registration Council (CPN), admitted into the membership of the Information Technology (Industry) Association of Nigeria and dully discharges its tax responsibly.
One of its most cherished accomplishments is the admission to the Association for Progressive Communication (APC) whose mandate is at the heart of the work. The membership has provided CITAD with a global network of partners, working on similar issues.

However, CITAD was also faced some key challenges that have affected the growth of organization. These include:  inadequately skilled manpower in a highly dynamic ICT sector, low professionalization of staffing, and low partnership with IT companies.

PAGE 2
12
LEAD CITAD—Five-Year Strategic Plan: 2018–2023
14

